Project Health Reporting Agent

Phase 1 — RAG Status Methodology (One Page)

## Approach

Project health is determined by a weighted composite score across six signals, each rated 0 (healthy) / 1 (at risk) / 2 (critical) and multiplied by its weight below. Weights sum to 100. The composite score is then banded into a RAG status, subject to override rules that can force a status regardless of the score — because one severe risk should never be diluted by five healthy metrics.

## Signals and Weights

| Signal | Weight | What it measures | How it's scored (0 / 1 / 2) |
| --- | --- | --- | --- |
| Schedule Slippage | 25 | Baseline vs. actual Start/Finish and Variance, weighted by Total Float (0 float = no slack to absorb delay). | 0 = on/ahead of baseline · 1 = slipping but float remains · 2 = slipping with zero float on a critical task |
| Milestone / Task Progress | 20 | % Complete compared against % of planned duration elapsed (Today's Date vs. Start/End Date), rolled up by Phase/Milestone. | 0 = complete% ≥ time-elapsed% · 1 = within 15 pts behind · 2 = more than 15 pts behind plan |
| Blockers | 20 | Open items surfaced in Status Comment / Comments sheet that are unresolved across more than one reporting cycle. | 0 = none open · 1 = open blocker(s) < 14 days old · 2 = any blocker open ≥ 14 days or blocking a critical task |
| Stakeholder Sentiment | 15 | Tone of PM/client free-text comments (LLM-assessed): confidence, frustration, escalation language, repeated asks. | 0 = neutral/positive · 1 = mild concern or friction language · 2 = escalation, repeated unresolved asks, or explicit frustration |
| Critical Path Exposure | 10 | Whether at-risk tasks sit on the critical path (Critical? = TRUE) versus tasks with slack. | 0 = no critical-path tasks at risk · 1 = one critical-path task at risk · 2 = multiple / cascading critical-path risk |
| Data Completeness / Confidence | 10 | Proportion of #UNPARSEABLE, blank, or missing fields in the source extract for this project. | 0 = <5% fields missing · 1 = 5–20% missing · 2 = >20% missing (status is a low-confidence estimate) |

## Composite → RAG Bands

| GREEN | AMBER | RED |
| --- | --- | --- |
| Composite score ≥ 80 | Composite score 50–79 | Composite score < 50 |

## Override Rules (bypass the composite score)

| Override Trigger | Forced Outcome |
| --- | --- |
| Any blocker open ≥ 21 days, unresolved across 3+ consecutive weekly reports | Force RED regardless of composite score |
| Zero-float critical task slipping by more than 20% of total project duration | Force RED regardless of composite score |
| Data completeness < 80% for the project extract | Cap status at AMBER maximum and flag as "Low Confidence" — insufficient data to certify Green |
| Agent-computed status disagrees with the source file's existing Schedule Health / RAG column by more than one band | Do not auto-resolve — surface both values side-by-side for PM/human review |

## Assumptions

- No budget/cost column exists in the source project plans (task-level Excel exports contain schedule and completion data only). “Budget burn” is therefore excluded from the score rather than estimated; it is noted as a data gap in every report so leadership knows the status reflects schedule and delivery health, not financial health.

- The existing “Schedule Health” / “RAG” columns already present in the source files are treated as one more input for comparison, not as ground truth — the agent computes its own independent status and flags disagreement rather than copying the existing label.

- Stakeholder sentiment is derived only from text already captured in the Status Comment and Comments sheet fields; no external channels (email, Slack, calls) are read.

- A task is only counted against schedule/progress signals if Not Applicable? is false and On Hold? is false, to avoid parked or excluded work being misread as stalled.

- Weights (25/20/20/15/10/10) reflect Professional-Services delivery norms — schedule and progress dominate because they are the most objective and client-visible signals — and are intended to be configurable per project type, not fixed constants.