## Slide 1
PMO EXECUTIVE SYNTHESIS
Portfolio Health Review
Monthly synthesis across 2 active engagement(s)
2
PROJECTS REVIEWED
45.0/100
PORTFOLIO AVG SCORE
2
RED-FLAGGED
10 Jul 2026
REPORT DATE

## Slide 2
Portfolio RAG Overview
Composite status is computed from schedule, milestone-progress, blocker, and data-quality signals.
Chart: 
| Green | Amber | Red
Projects | 0 | 0 | 2
2
TOTAL PROJECTS
0
GREEN
0
AMBER
2
RED
• Current mix: 2 Red.
• Status reflects schedule, milestone, and blocker health; financial/budget health is out of scope for this data set.
Project Health Reporting Agent – Confidential
1 / 4

## Slide 3
Project-by-Project Snapshot
RED
Zycus - Titan S2P Implementation
Schedule Slippage: Worst task-level schedule variance is -81 day(s) on a zero-float (critical) task.
⚠ PM-reported status: Green — flagged for review
40
/ 100
RED
Zycus - UniSan S2P Implementation
Schedule Slippage: Worst task-level schedule variance is -2 day(s) on a zero-float (critical) task.
50
/ 100
Project Health Reporting Agent – Confidential
2 / 4

## Slide 4
Emerging Risks & Cross-Project Themes
Cross-project risk categories, ranked by severity — not a per-project status recap.
CRITICAL
Critical-Path Concentration
15 critical-path (zero-float) tasks are currently slipping across 2 projects simultaneously — portfolio-wide delivery-capacity risk, not a single-project scheduling issue.
Affects: Zycus - Titan S2P Implementation, Zycus - UniSan S2P Implementation
HIGH
Recurring Delivery Theme
Root cause 'critical-path slippage' appears independently across 2 projects, suggesting a shared process gap rather than isolated project execution issues.
Affects: Zycus - Titan S2P Implementation, Zycus - UniSan S2P Implementation
HIGH
Governance / Reporting Integrity
PM-reported status disagrees with the independently computed status on 1 project(s) by more than one band — a signal that self-reported status may be optimistic and should not be forwarded to clients unreviewed.
Affects: Zycus - Titan S2P Implementation
MEDIUM
Data Confidence
Core schedule fields are under 80% populated on 1 project(s) — computed RAG status on these carries reduced statistical confidence and is capped at Amber-or-worse by design.
Affects: Zycus - UniSan S2P Implementation
Project Health Reporting Agent – Confidential
3 / 4

## Slide 5
Recommendations & Decisions Needed
Prioritized by urgency — P1 acts this week, P3 is a systemic/process fix.
P1 – THIS WEEK
Escalate Zycus - Titan S2P Implementation to delivery leadership this week.
Owner: Delivery Lead · Zycus - Titan S2P Implementation
Schedule Slippage: Worst task-level schedule variance is -81 day(s) on a zero-float (critical) task.
P1 – THIS WEEK
Escalate Zycus - UniSan S2P Implementation to delivery leadership this week.
Owner: Delivery Lead · Zycus - UniSan S2P Implementation
Schedule Slippage: Worst task-level schedule variance is -2 day(s) on a zero-float (critical) task.
P1 – THIS WEEK
Reconcile PM-reported vs. computed status on Zycus - Titan S2P Implementation before any client-facing communication.
Owner: PMO / Governance · Zycus - Titan S2P Implementation
Source file status disagrees with independently computed RAG by more than one band.
P2 – NEXT REVIEW
Institute a portfolio-wide critical-path review cadence (weekly, cross-project) rather than handling each slipping task in isolation.
Owner: PMO / Governance · Portfolio-wide
15 critical-path (zero-float) tasks are currently slipping across 2 projects simultaneously — portfolio-wide delivery-capacity risk, not a single-project scheduling issue.
P3 – PROCESS FIX
Request updated baseline/variance fields from delivery teams on projects below the data-completeness floor; low-confidence status should not be treated as final.
Owner: PMO / Governance · Zycus - UniSan S2P Implementation
Core schedule fields are under 80% populated on 1 project(s) — computed RAG status on these carries reduced statistical confidence and is capped at Amber-or-worse by design.
Project Health Reporting Agent – Confidential
4 / 4