| WEEKLY PROJECT HEALTH REPORT Zycus - Titan S2P Implementation Week Ending 2026-07-10 | RAG STATUS RED Composite Score: 40.0 / 100 |
| --- | --- |

FLAGGED FOR REVIEW — the source file's own Schedule Health/RAG label is "Green", but this agent independently computed "Red". Computed status disagrees with source file's existing RAG/Schedule Health by more than one band - flagged for PM review, not auto-resolved.

OVERRIDE RULES TRIGGERED

Blocker open >= 21 days -> forced RED

Zero-float critical task slipping -> forced RED

WHY THIS STATUS

This project is currently Red based on 3 key factor(s): Schedule Slippage: Worst task-level schedule variance is -81 day(s) on a zero-float (critical) task. Blockers: 5 open blocker/friction reference(s) found in comments with at least one open 14+ days. Recommend immediate escalation to the delivery lead and client-facing communication.

TOP DRIVERS

Schedule Slippage: Worst task-level schedule variance is -81 day(s) on a zero-float (critical) task.

Blockers: 5 open blocker/friction reference(s) found in comments with at least one open 14+ days.

Critical Path Exposure: 14 critical-path task(s) currently slipping.

SIGNAL BREAKDOWN

| Signal | Score | Detail |
| --- | --- | --- |
| Schedule Slippage | 2 | Worst task-level schedule variance is -81 day(s) on a zero-float (critical) task. |
| Progress Vs Plan | 0 | 71% complete vs 57% of planned duration elapsed (-14 pt gap). |
| Blockers | 2 | 5 open blocker/friction reference(s) found in comments with at least one open 14+ days. |
| Stakeholder Sentiment | 0 | 0/16 comments contain friction/escalation language. |
| Critical Path Exposure | 2 | 14 critical-path task(s) currently slipping. |
| Data Completeness | 1 | 81% of core fields populated. |

Score: 0 = healthy   ·   1 = at risk   ·   2 = critical

RECOMMENDED ACTIONS

Escalate to delivery leadership immediately.

Convene a recovery-plan session with the client.

Re-sequence or add resources to the blocking critical-path task(s).

STAKEHOLDER SENTIMENT

Score: 0 (0 = neutral/positive, 2 = escalation) — Derived from keyword-based fallback scan (no LLM provider configured).

Data completeness: 81%.  Generated by: fallback_template (reason: No LLM_PROVIDER/API key configured (see .env.example).)