| WEEKLY PROJECT HEALTH REPORT Zycus - UniSan S2P Implementation Week Ending 2026-07-10 | RAG STATUS RED Composite Score: 50.0 / 100 |
| --- | --- |

OVERRIDE RULES TRIGGERED

Zero-float critical task slipping -> forced RED

Data completeness 67% < 80% -> capped at AMBER (low confidence)

WHY THIS STATUS

This project is currently Red based on 3 key factor(s): Schedule Slippage: Worst task-level schedule variance is -2 day(s) on a zero-float (critical) task. Data Completeness: 67% of core fields populated. Recommend immediate escalation to the delivery lead and client-facing communication.

TOP DRIVERS

Schedule Slippage: Worst task-level schedule variance is -2 day(s) on a zero-float (critical) task.

Data Completeness: 67% of core fields populated.

Progress Vs Plan: 44% complete vs 59% of planned duration elapsed (15 pt gap).

SIGNAL BREAKDOWN

| Signal | Score | Detail |
| --- | --- | --- |
| Schedule Slippage | 2 | Worst task-level schedule variance is -2 day(s) on a zero-float (critical) task. |
| Progress Vs Plan | 1 | 44% complete vs 59% of planned duration elapsed (15 pt gap). |
| Blockers | 0 | 0 open blocker/friction reference(s) found in comments. |
| Stakeholder Sentiment | 0 | No stakeholder comments available; assuming neutral. |
| Critical Path Exposure | 1 | 1 critical-path task(s) currently slipping. |
| Data Completeness | 2 | 67% of core fields populated. |

Score: 0 = healthy   ·   1 = at risk   ·   2 = critical

RECOMMENDED ACTIONS

Escalate to delivery leadership immediately.

Convene a recovery-plan session with the client.

Re-sequence or add resources to the blocking critical-path task(s).

STAKEHOLDER SENTIMENT

Score: 0 (0 = neutral/positive, 2 = escalation) — Derived from keyword-based fallback scan (no LLM provider configured).

Data completeness: 67%.  Generated by: fallback_template (reason: No LLM_PROVIDER/API key configured (see .env.example).)